## Project_Info
Project Name: | Cartify
Client: | DEPI Mega Project
Created By: | Team 50
Creation Date: | 2025-05-11
Reviewed by: | Team 50
Type of Testing: | Exprolaroty, Excuting Test cases

## Requirements
ID | Domain Owner | Functional Requirement (FR) Description | Priority | Test Scope
FR-U-001 | Abdallah Mohamed (User Pages) | The system must allow a new user to complete the registration process using a unique email and valid password (min. 8 chars). | High | Functional
FR-U-002 | Abdallah Mohamed (User Pages) | The system must prevent login attempts with incorrect credentials, showing a clear, specific error message. | High | Security
FR-U-003 | Abdallah Mohamed (User Pages) | The profile page must visually confirm when an update (e.g., address change) has been saved successfully. | Medium | Usability
FR-U-004 | Abdallah Mohamed (User Pages) | The password recovery link/form must handle valid email submissions by displaying a confirmation message about the email sent. | Medium | Functional
FR-S-005 | Eslam Elhosany (Shopping) | The main Products page must display products in an organized grid/list with image, name, and price visible. | High | Usability
FR-S-006 | Eslam Elhosany (Shopping) | The search bar must return relevant results based on keywords (e.g., name, brief description). If no results are found, a clear "No Results" message must be displayed. | High | Functional
FR-S-007 | Eslam Elhosany (Shopping) | The product filtering options (e.g., Category, Price Range) must instantly update the product list without a full page reload. | Medium | Performance
FR-S-008 | Eslam Elhosany (Shopping) | Product availability status (In Stock/Out of Stock) must be clearly visible on the Product Details page. | High | Functional
FR-C-009 | Zeina Salem (Cart & Orders) | The "Add to Cart" function must immediately update the cart item count displayed in the navigation bar. | High | Functional
FR-C-010 | Zeina Salem (Cart & Orders) | The Cart page must allow the user to easily adjust the quantity or remove any item, with the subtotal updating dynamically. | High | Functional
FR-C-011 | Zeina Salem (Cart & Orders) | The Checkout steps (Shipping, Payment, Review) must be clearly displayed and navigable (e.g., step indicators). | High | Usability
FR-C-012 | Zeina Salem (Cart & Orders) | The Order Tracking page must display the current status (e.g., Shipped, Delivered) and an estimated delivery date/timeline. | High | Functional
FR-A-013 | Eslam Nowar (Account) | The user's Profile page must allow updates to personal information (e.g., name, address) upon successful submission. | Medium | Functional
FR-A-014 | Eslam Nowar (Account) | The Wishlist page must accurately list all saved products and allow easy removal of an item. | High | Functional
FR-A-015 | Eslam Nowar (Account) | The Notifications page must display recent, unread notifications (e.g., item back in stock, order status updates). | Medium | Functional
FR-A-016 | Eslam Nowar (Account) | A logged-in user must have a "Logout" option clearly visible in the header menu or profile dropdown. | High | Usability
FR-M-017 | Sarah Elzaeiny (Merchant/Support) | The "Merchant Signup" form must validate all required fields (e.g., valid email, business name) before allowing submission. | High | Functional
FR-M-018 | Sarah Elzaeiny (Merchant/Support) | The "Help & Support" page must contain accurate and working links/buttons to support resources (e.g., FAQ, Contact Form). | High | Usability
FR-M-019 | Sarah Elzaeiny (Merchant/Support) | The Merchant Home dashboard must display summarized key metrics (e.g., total sales, recent orders) using mock data/placeholders. | Medium | Functional
NFR-020 | Team (General) | Performance: All critical pages (Product Details, Cart) must load visual content within 3 seconds. | Medium | Performance
NFR-021 | Team (General) | Responsiveness: All pages must display correctly and functionally on both desktop and mobile views (no horizontal scrolling). | High | Usability

## User_Stories
ID | Owner | User Story | Acceptance Criteria (AC)
US-U-01 | Abdallah Mohamed | As a new user, I want to see clear requirements for my password when signing up so that I don't fail registration due to policy errors. | AC: The registration form indicates that the password requires at least 8 characters and includes a mix of case/numbers. AC: If the password fails criteria, an inline error message appears before submission.
US-U-02 | Abdallah Mohamed | As a user, I want to be able to edit my name and shipping address so that my orders go to the right place. | AC: The Profile page loads pre-filled data. AC: Saving changes redirects or displays a success banner.
US-S-03 | Eslam Elhosany | As a shopper, I want to be able to sort the products (e.g., by Price Low to High, Newest) so that I can prioritize what I see first. | AC: A visible dropdown for sorting is present on the Products page. AC: Selecting a sort option re-orders the products instantly.
US-S-04 | Eslam Elhosany | As a shopper, I want to clearly see high-resolution images of the product on the details page so that I can inspect the item quality before buying. | AC: Clicking a small product image thumbnail displays the corresponding high-resolution image in the main viewing area.
US-C-05 | Zeina Salem | As a customer, I want the cart summary to clearly calculate the subtotal, shipping, and taxes so that I know the full cost before I enter payment info. | AC: The Cart and Checkout review pages display separate line items for Subtotal, Estimated Shipping, and Grand Total.
US-C-06 | Zeina Salem | As a customer, I want to receive confirmation that my order was placed so that I know the transaction was successful. | AC: Upon final confirmation, the user is redirected to a dedicated "Order Confirmation" page displaying the order number.
US-A-07 | Eslam Nowar | As a user, I want to see an icon indicating when I have unread notifications so that I don't miss important updates. | AC: The Notifications icon in the header displays a numbered badge if unread notifications exist. AC: Clicking the icon removes the badge.
US-A-08 | Eslam Nowar | As a user, I want to be able to move an item directly from my Wishlist to my Shopping Cart so that I can purchase saved items quickly. | AC: A clear "Add to Cart" button exists next to each Wishlist item. AC: Clicking it adds the item to the cart and removes it from the Wishlist.
US-M-09 | Sarah Elzaeiny | As a new merchant, I want the signup process to be straightforward and simple so that I can join the platform without hassle. | AC: The Merchant Signup form is contained on a single page or a clear, short multi-step process. AC: All required fields are clearly marked with an asterisk (*).
US-M-10 | Sarah Elzaeiny | As a user needing help, I want the help page to be organized by topic (e.g., Orders, Returns, Account) so that I can quickly locate relevant answers. | AC: The Help & Support page uses distinct, clickable sections/accordions based on common user topics.

## Test_Cases
TC_ID | Feature | Req ID | Title | Description | Preconditions | Test Steps | Test Data | Expected Result | Postconditions | Actual Result | Status | Author | Execution Cycle | Priorty
TC-U-1.1 | Registration | FR-U-001 | Valid Registration Submission | Verify a new user can successfully register using unique and valid required data. | Stable internet connection; Website is up and running. | 1. Navigate to register.html. 2. Enter unique valid email, password (≥8 chars), and required user data. 3. Click 'Next'. | Email: newuser@test.com, Pass: ValidPass123@ | User is successfully registered and is redirected to the Personal info form. | New user record exists in the system. | N/A | Passed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-1.6 | Registration | FR-U-001 | Empty Required Field | Verify the system prevents registration if any mandatory field (e.g., email or password) is left blank. | Stable internet connection; Website is up and running. User is on login.html. | 1. Fill in all fields except the Email field. 2. Click 'Next'. | Email: (blank), Pass: ValidPass123 | The system prevents submission and displays an inline error message says "❗ All fields are required" . | User remains on the Registration page. | N/A | Passed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-1.7 | Registration | FR-U-001 | Password Minimum Length Check | Verify the system enforces the minimum password length of 8 characters during registration. | Stable internet connection; Website is up and running. User is logged in and on profile.html. | 1. Fill all fields with valid data. 2. Enter a password that is 7 characters or less. 3. Click 'Next'. | Pass: short12 | The system prevents submission, and an error message says "❌ Password must be 8+ chars with uppercase, lowercase, number,special char" | User remains on the Registration page. | N/A | Passed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-1.2 | Login | FR-U-002 | Login: Incorrect Password Check | Verify the system denies access and provides a specific error message when the password is wrong. | Stable internet connection; Website is up and running. User is on the public internet. | 1. Enter a valid registered email. 2. Enter a deliberately incorrect password. 3. Click 'Login'. | Email: existing@user.com, Pass: WrongPass123 | Login fails, and a clear, specific error message ( "❌ Wrong username or password!") is displayed on the page. | User remains on the Login page. | N/A | Passed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-2.4 | Login | FR-U-002 | Login: Non-existent User Error | Verify the system prevents login for non-existent users without giving away sensitive account information. | Stable internet connection; Website is up and running. | 1. Enter an email that is not registered. 2. Enter any password. 3. Click 'Login'. | Email: nonexistent@test.net | Login fails. A generic error message is displayed ("❌ Wrong username or password!") to protect against account enumeration. | User remains on the Login page. | N/A | Passed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-2.5 | Login | FR-U-002 | Password Case Sensitivity | Verify that the login process correctly enforces password case sensitivity. | Stable internet connection; Website is up and running. User is on register.html. | 1. Enter a valid registered email. 2. Enter the correct password but change the case of one letter. 3. Click 'Login'. | Pass: TeStPaSs123@ (incorrect casing) | Login fails, and an error message "❌ Wrong username or password!" is displayed, proving the system is case-sensitive. | User remains on the Login page. | N/A | Passed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-1.4 | Recovery | FR-U-004 | Password Recovery Request | Verify the system processes a valid password recovery request by confirming the email link has been sent. | Stable internet connection; Website is up and running. User is on register.html. | 1. Navigate to the "Forgot Password" link/page. 2. Enter a valid, registered email address. 3. Click 'Submit'/'Recover'. | Email: newuser@test.com | A confirmation message displays, stating that a recovery link has been sent to the specified email address. | User remains on the recovery form or is redirected to a confirmation page. | After clicking on the " forget password link and entering a valid email, an error message appears:" ❌ Enter a valid email or server error," preventing the user from continuing the process | Failed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-4.3 | Recovery | FR-U-004 | Recovery: Unregistered Email | Verify that entering an unregistered email for recovery does not confirm the account's existence. | Stable internet connection; Website is up and running. User is on login.html. | 1. Enter an email address that is not registered. 2. Click 'Submit'/'Recover'. | Email: unknown@test.com | A generic message confirms the process ("❌ Enter valid email or server error") without confirming account existence. | User is protected from enumeration attacks. | N/A | Passed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-1.3 | Profile | FR-U-003 | Profile Update Confirmation | Verify that successful profile updates (e.g., address change) are visually confirmed to the user. | Stable internet connection; Website is up and running. User is on login.html. | 1. Navigate to the Profile page. 2. Modify the address or phone number field. 3. Click 'Save' or 'Update'. | New Address: 123 Test Street | A visual confirmation (e.g., a success banner or pop-up) appears, and the new data persists on the screen. | Profile fields are updated in the UI. | Can't complete the process because when I click on profile, the pop-up message says I need to log in first to see the profile, although I logged in | Failed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-3.3 | Profile | FR-U-003 | Profile Update: Data Persistence | Verify that changes made to the profile page are correctly saved and loaded back upon return. | Stable internet connection; Website is up and running. User is logged in and on profile.html. | 1. Execute TC-U-1.3 (Profile Update). 2. Navigate to another page (e.g., Products). 3. Return to profile.html. | New Data: (from previous step) | The newly saved information is still displayed in the profile fields, confirming persistence. | Profile data integrity is confirmed. | Can't complete the process because when I click on profile, the pop-up message says I need to log in first to see the profile, although I logged in | Failed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-1.5 | Responsiveness | NFR-021 | Mobile Form Responsiveness | Verify the Login and Registration forms are fully usable and display correctly on mobile screens. | Stable internet connection; Website is up and running. User is on the "Forgot Password" form. | 1. View login.html and register.html in an Android/mobile emulator. 2. Attempt to input data into the forms. | Device: Android/Chrome Emulator | Forms, buttons, and text scale appropriately; input fields are accessible; no horizontal scrolling occurs. | None. |  | Passed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-U-5.2 | Responsiveness | NFR-021 | Responsiveness: Profile Page on Mobile | Verify the Profile page layout and update forms are correctly rendered and usable on small screens. | Stable internet connection; Website is up and running. User is logged in. | 1. View profile.html in an Android/mobile emulator. 2. Attempt to edit and save a field. | Device: Android/Chrome Emulator | All fields and the 'Save' button are clearly visible and accessible; the layout is vertical and functional. | None. |  | Passed | Abdallah | Sprint 1: Core Flow Execution V_1.0
TC-ACC-WL-1.1 | Account (wishlist) |  | prodcut data uploaded to wishlist | Verify the products data updatated to WISHLIST | Stable internet connection; Website is up and running. | 1-open the site 2-log in with my account 3-click to Hamburger Menu Icon 4-click to product 5-add products 6-go to Hamburger Menu Icon 7-go to wishlist | Device: Android/Chrome device :windows 11pro | all product will uploaded to wishlist with these photos |  | photos of products don't uploaded | Failed | Eslam Nawar | Sprint 1: Core Flow Execution V_1.0
TC-ACC-NOT-1.1 | Account (NotificTION) |  | Notifications from the systems are deleted | Verify when system send us notifications and we delete it ,it will delete | Stable internet connection; Website is up and running. | 1-open the site 2-log in with my account 3-clich to Notifications | Device: Android/Chrome device :windows 11pro | when we delete notifications,it will delete |  | notification will delete | Passed | Eslam Nawar | Sprint 1: Core Flow Execution
TC-ACC-WL-1.2 | Account (wishlist) |  | product from wishlist uploaded to my cart | verify products from my wishlist when we clic "move to cart ",they will uploaded succfully | Stable internet connection; Website is up and running. | 1- open the site 2-log in with account 3-add some prodcut to wishist 4-go to wishlist | Device: Android/Chrome device :windows 11pro | salary will uploaded and items will up loaded |  | salary and item in my cart willnot uploaded | Failed | eslam nawar | V_1.0
TC-Auth-Token-001 | authentication |  | User should be logged out when token becomes invalid or expires |  | User is already logged in. A valid session token exists in the browser (local storage or cookies). | 1-Log in to the website using valid user credentials. 2-Keep using the system until the token expiration time passes 3-Perform any action that triggers an API request 4-Observe the system behavior when the invalid/expired token is sent. | device :windows 11pro | the user will not logout |  | user will logout | Failed | eslam nawar | Sprint 1: Core Flow Execution
TC-ACC-WL-1.3 | Account (wishlist) |  | user can delete products form wishlist or not | Verify whether the user is able to delete products from the wishlist successfully. | Stable internet connection; Website is up and running. | 1-log in with your account 2-add some producuts to your wishlist 3-delete some products | device :windows 11pro | the product should be removed from the wishlist | none | the product will be removed from the wishlist | Passed | eslam nawar | Sprint 1: Core Flow Execution
TC-ACC-WL-1.4 | Account (wishlist) |  | "cintinue shooping "button | Verify "continue shopping "button is running when wishlist is empty | Stable internet connection; Website is up and running. | 1-log in with your account 2-delete all products from your wishlist 3-click on "continue shopping" | device :windows 11pro | user will return to the main page | none | user will returm to the main page | Passed | eslam nawar | Sprint 1: Core Flow Execution
TC-ACC-WL-1.5 | Account (wishlist) |  | Wishlist persists after logout | Wishlist should remain saved after the user logs out and logs in again |  | Log in using valid credentials. 2-Navigate to any product page. 3-Click “Add to Wishlist” for one or more products. 4-Go to the Wishlist Page and confirm the products appear. 5-Log out from the account. 6-Log in again using the same user credentials. 7-Navigate to the Wishlist Page. | device :windows 11pro | The products added previously should still be displayed in the wishlist. Wishlist data should not be cleared after logout. The system should not require re-adding the items. |  |  | Passed | eslam nawar | Sprint 1: Core Flow Execution
TC-PRP-001 | Products Page | FR-S-005 | Load Products Page | Verify that the Products page loads successfully |  | 1. Navigate to Products page | N/A | Products page opens without errors | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.0 | High
TC-PRP-002 | Products Page | FR-S-005 | Display Products in Grid/List | Verify products are displayed in an organized grid/list format | Products exist in database | 1. Open Products page | Sample products in DB | Products are displayed in organized grid/list | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.1 | High
TC-PRP-003 | Products Page | FR-S-005 | Product Image Visibility | Verify product image is visible for each product | Products have images | 1. Open Products page | Products with images | Each product displays an image | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.2 | High
TC-PRP-004 | Products Page | FR-S-005 | Product Name Visibility | Verify product name is visible for each product | Products have names | 1. Open Products page | Products with names | Each product displays its name | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.3 | High
TC-PRP-005 | Products Page | FR-S-005 | Product Price Visibility | Verify product price is visible for each product | Products have prices | 1. Open Products page | Products with prices | Each product displays its price | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.4 | High
TC-PRP-006 | Products Page | FR-S-005 | Product Rate Visibility | Verify product Rate is visible for each product | Products have Rates | 1. Open Products page | Products with Rate | Each product displays its Rate | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.5 | High
TC-PRP-007 | Products Page | FR-S-005 | Search Bar Visibility | Verify search bar is visible | Products page accessible | 1. Navigate to Products page | N/A | Search bar appears at top | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.6 | Medium
TC-PRP-008 | Products Page | FR-S-005 | Cart Button Visibility | Verify “Go to Cart” button appears | Products page accessible | 1. Open Products page | N/A | Cart button visible in header | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.7 | low
TC-PRP-009 | Products Page | FR-S-005 | Wishlist Button Visibility | Verify Wishlist button appears | Products page accessible | 1. Open Products page | N/A | Wishlist button visible in header | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.8 | low
TC-PRP-010 | Products Page | FR-S-005 | Product Rating Icon | Verify star rating displayed | Products have rating | 1. Open Products page | Products with ratings | Star icon + rating appear | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.9 | low
TC-PRP-011 | Products Page | FR-S-005 | Logo Visibility | Verify header logo visibility | N/A | 1. Open Products page | N/A | Logo visible in header | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.10 | low
TC-PRP-012 | Products Page | FR-S-005 | Menu Icon Visibility | Verify burger menu icon in header | N/A | 1. Open Products page | N/A | Menu icon visible | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.11 | Medium
TC-PRP-013 | Products Page | FR-S-005 | Product Card Styling | Verify card design and styling | Products exist | 1. Open Products page | N/A | Card shadow + rounded corners visible | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.12 | Medium
TC-PRP-014 | Products Page | FR-S-005 | Empty Products State | Verify empty state message when no products exist | Database has no products | 1. Open Products page | Empty database | Page shows "No products available" message | None | Blocked , data is already static | Rejected | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.13 | Medium
TC-PRP-015 | Products Page | FR-S-005 | Default Product Order | Verify default order of products | Products exist in database | 1. Open Products page | Multiple products | Products displayed in default organized order | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.14 | Medium
TC-PRP-016 | Products Page | FR-S-005 | Responsive Layout | Verify page layout adjusts on different devices/screens | Products exist | 1. Open Products page2. Resize browser window | N/A | Grid/list layout adjusts correctly on all screen sizes | None | buttons overlap , Sort btn not inaccessible | Failed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.15 | Medium
TC-PRP-017 | Products Page | FR-S-005 | Product Link Navigation | Verify each product link is clickable and navigates to detail page | Products exist with valid links | 1. Open Products page2. Click on a product | N/A | User navigated to product detail page | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.16 | High
TC-PRP-018 | Products Page | FR-S-005 | Image Load Check | Verify product images load properly without broken links | Products have images stored correctly | 1. Open Products page | Products with images | All product images load without broken icons | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.17 | High
TC-PRP-019 | Products Page | FR-S-005 | Empty Products State | Verify empty state message when no products exist | Database has no products | 1. Open Products page | Empty database | Page shows "No products available" message | None | Blocked , data is already static | Rejected | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.18 | Medium
TC-PRP-020 | Products Page | FR-S-006 | Search Functionality | Verify search filters products correctly | Products exist | 1. Enter keyword in search bar2. Click Search | Example: Product 1 | Only matching products appear | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.23 | High
TC-PRP-021 | Products Page | FR-S-005 | Add to Cart Button | Verify each product has Add to Cart button | Products exist | 1. Open Products page | N/A | Each product shows Add to Cart button | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.24 | High
TC-PRP-022 | Products Page | FR-S-005 | Add to Wishlist Button | Verify Wishlist button for each product | Products exist | 1. Open Products page | N/A | Each product shows Add to Wishlist button | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.25 | High
TC-PRP-023 | Products Page | FR-S-005 | Active Page Display | Verify the current page number is highlighted | N/A | 1. Observe the pagination area. | N/A | The current page number (e.g., 2) is clearly highlighted/active (Green color). | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.26 | Low
TC-PRP-024 | Products Page | FR-S-005 | Next Page Navigation | Verify "Next" button moves to the next page | Current page is not the last page (e.g., Page 2) | 1. Click the "Next" button. | N/A | Page 3 content loads, and the number 3 is highlighted. | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.27 | Low
TC-PRP-025 | Products Page | FR-S-005 | Previous Page Navigation | Verify "Prev" button moves to the previous page | Current page is not the first page (e.g., Page 2) | 1. Click the "Prev" button. | N/A | Page 1 content loads, and the number 1 is highlighted. | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.28 | Low
TC-PRP-026 | Products Page | FR-S-005 | Direct Page Navigation | Verify direct navigation by clicking page number | N/A | 1. Click the page number 3. | N/A | Page 3 content loads, and the number 3 is highlighted. | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.29 | Low
TC-PRP-027 | Products Page | FR-S-005 | "Prev" Button State (First Page) | Verify "Prev" button is disabled on the first page | Currently on Page 1 | 1. Navigate to Page 1. 2. Attempt to click the "Prev" button. | N/A | The "Prev" button is disabled (or grayed out) and does not respond to clicks. | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.30 | Low
TC-PRP-028 | Products Page | FR-S-005 | "Next" Button State (Last Page) | Verify "Next" button is disabled on the last page | Currently on Page 3 (assuming 3 is the last page) | 1. Navigate to Page 3. 2. Attempt to click the "Next" button. | N/A | The "Next" button is disabled (or grayed out) and does not respond to clicks. | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.31 | Low
TC-SRT-001 | Products Page | FR-S-007 | Verify instant product Price Sorting without page reload | Ensure product list updates instantly when applying price Sorting | User logged in or guest user on Products page | Open Products page → Click On Sort Dropdown → Apply Price Sorting | NA | Product list updates instantly without full page reload | Products sorted by Price from low to high price | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.32 | Medium
TC-SRT-002 | Products Page | FR-S-007 | Verify instant product Rate Sorting without page reload | Ensure product list updates instantly when applying rate Sorting | User logged in or guest user on Products page | Open Products page → Click On Sort Dropdown → Apply Rate Sorting | NA | Product list updates instantly without full page reload | Products sorted by Rate from low to high price | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.33 | Medium
TC-SRT-003 | Products Page | FR-S-007 | Verify Sorting response time is less than 1 second |  | User on Products page | Select any Sorting option and measure response time | Any Sorting option | Product list updates in < 1 sec | N/A | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.34 | Medium
TC-SRT-004 | Products Page | US-S-03 | Verify sorting dropdown is visible | Ensure sorting options are visible on the products page | User on Products page | Open Products page and locate sorting dropdown | N/A | Sorting dropdown is visible with multiple options | N/A | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.35 | High
TC-PRD-001 | Product Details | FR-S-008 | Verify In Stock/Out of Stock visibility | Validate that product availability is clearly displayed | Product exists in database | Open Product Details page and check stock label | Product with stock = 0 or >0 | Clear label shows “In Stock” or “Out of Stock” | N/A | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.36 | High
TC-PRD-002 | Product Details | US-S-04 | Verify clicking thumbnail loads high-resolution image | Ensure product thumbnails display high-resolution images when clicked | Product has multiple images | Open Product Details → Click on a thumbnail → Observe main image | Thumbnail image set | Main image updates with high-resolution version | N/A | Thumbnail Not Reload and Not Clickable | Failed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.37 | High
TC-PRD-003 | Product Details |  | Verify Product Card UI Elements | Verify that all elements (Name, Image, Price, Desc, Buttons) are visible and aligned correctly. | User is on the product listing page. | 1. Navigate to the product page. 2. Inspect the product card layout. | N/A | Product Name, Image, Price, Description, Stock status, and 3 buttons should be visible (Add to cart , But Now , Add to wish list ) . | Page loaded successfully. | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.38 | High
TC-PRD-004 | Products Page | FR-S-005 | Menu Icon Visibility | Verify burger menu icon in header | N/A | 1. Open Products page 2. Click in any Product | N/A | Menu icon visible | None | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.11 | Medium
TC-PRD-005 | Product Details |  | Verify Product Image Loading | Ensure the product image loads correctly without broken icons. | Internet connection is active. | 1. Load the page. 2. Check the "Product Image" area. | N/A | The actual product image should load clearly. It should not show a broken link icon or alt text only. | Image displayed. | Image Not loaded | Failed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.39 | High
TC-PRD-006 | Product Details |  | Verify Price Formatting | Ensure the price is displayed with the correct currency and decimal places. | Product exists in DB. | 1. Observe the price label. 2. Check for currency symbol. | N/A | Price should be displayed with currency. | N/A | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.40 | Medium
TC-PRD-007 | Product Details |  | Verify "Add to Cart" Functionality | Validate that clicking the button adds the item to the cart. | User is on the page. | 1. Click on "Add to Cart" button. 2. Check the cart counter/icon. | N/A | Redirect to Cart page. |  | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.41 | High
TC-PRD-008 | Product Details |  | Verify "Buy Now" Functionality | Validate that clicking the button redirects to the checkout page. | User is on the page. | 1. Click on "Buy Now" button. | N/A | User should be immediately redirected to the Checkout/Payment page with the item. |  | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.42 | High
TC-PRD-009 | Product Details |  | Verify "Add to Wishlist" Functionality | Validate adding the item to the user's wishlist. | User is logged in | 1. Click on "Add to Wishlist" button. | N/A | Redirect to wish list. |  | TBA | Passed | Eslam Elhosany | Sprint 1: Core Flow Execution V_1.43 | High
TC-C-001 | Cart page | NFR-020 | Cart page loads successfully | Verify that the cart page opens normally without errors | User is logged in | 1. Open the website 2. Click on the Cart icon | N/A | The Cart Page displays correctly, all items are shown, and buttons (e.g., checkout, delete) are visible and functional | User is on the Cart Page, and the system is ready for further actions | Cart page opens successfully and displays normally | Passed | Zeina Salem | Sprint 1: Core Flow Execution | Medium
TC-C-002 | Cart page | FR-C-010 | Empty Cart – Display message | Verify that the empty cart shows the correct placeholder message | User is logged in, and the cart has no items | 1. Navigate to Cart page | N/A | Cart displays “Your cart is empty” message | User is on the empty Cart Page, and the system is ready for further actions | Cart displays empty state with the correct empty-cart message | Passed | Zeina Salem | Sprint 1: Core Flow Execution | High
TC-C-003 | Cart page | FR-C-010 | “Start Shopping” redirects user to products | Verify that the “Start Shopping” button redirects to the product listing | User is on the empty Cart Page | 1. Click the "Start Shopping" button | N/A | The user is redirected to the Products Page | User is on the wrong page (Home Page) | The user is redirected to the Home Page instead of the Products Page | Failed | Zeina Salem | Sprint 1: Core Flow Execution | High
TC-C-004 | Cart page | FR-C-009 | Unable to add product to cart | Verify that the user can add a product to the cart. The Products Page does not display any products. | User is logged in and navigating to Products Page to add an item to the cart | 1.Navigate to the" Products Page." 2. Attempt to add any product to the cart | N/A | Products should be displayed and the user should be able to click Add to Cart | User is stuck on the Products Page with no possible way to add items to the cart | No products are displayed → User cannot perform Add to Cart → Cart testing cannot continue. | Not_Executed | Zeina Salem | Sprint 1: Core Flow Execution | Critical
TC-C-005 | Cart page | FR-C-010 | Cart shows incorrect item count | Verify that the cart displays accurate number of items based on actual added products | User is logged in, and the cart has no items | 1.Navigate to the Products Page. 2.Check the product list. 3.Open the Cart Page. | N/A | Cart item count should match the actual items added (should be 0 ) | User is on the Cart Page with incorrect item count. | Cart shows 3 items in subtotal even though Products Page shows no items. | Failed | Zeina Salem | Sprint 1: Core Flow Execution | Critical
TC-C-006 | Cart page | FR-C-10 | Proceed to Checkout button functionality | Verify that clicking the Proceed to Checkout button redirects the user to the checkout page | User is on the Cart Page | 1Open the Cart Page. 2.Click the Proceed to Checkout button | N/A | User should be redirected to the Checkout Page | User remains stuck on the Cart Page. | Button is not working and no action happens | Failed | Zeina Salem | Sprint 1: Core Flow Execution | High
TC-C-007 | Cart page | FR-C-10 | Continue Shopping button functionality | Verify that clicking Continue Shopping redirects the user back to the Products Page | User is on the Cart Page | 1Open the Cart Page. 2.Click the Continue Shopping button | N/A | User should be redirected to the Products Page. | User is still on the Cart Page | Button is not working — no redirection | Failed | Zeina Salem | Sprint 1: Core Flow Execution | Medium
TC-C-008 | Checkout page | FR-C-11 | Checkout form shows error when required field is empty | Verify that leaving a required checkout field empty shows a validation message | User is on Checkout Page (Cart has items or assume cart is pre-filled) | 1.Navigate to Checkout Page. 2.Leave a required field empty. 3.Fill other required fields. 4.Click Submit / Place Order. | Leave any required field empty | System shows message: “Please fill this field” or equivalent validation message. Checkout is not submitted | User remains on Checkout Page; field needs to be filled to continue | Message appears as expected | Passed | Zeina Salem | Sprint 1: Core Flow Execution | Medium
TC-C-009 | Checkout page | FR-C-11 | Checkout shows “Your cart is empty” for Cash on Delivery | Verify that attempting to submit checkout with empty cart using Cash on Delivery shows correct message | User is logged in, Cart is empty | 1.Navigate to Checkout Page. 2.Select Cash on Delivery. 3.Click Submit / Place Order | Select payment method = Cash on Delivery. Fill other required checkout fields | System shows “Your cart is empty” message. Checkout is not processed. | User remains on Checkout Page. | Message appears as expected | Passed | Zeina Salem | Sprint 1: Core Flow Execution | High
TC-C-010 | Checkout page | FR-C-11 | Checkout allows submit with empty credit card / PayPal data but cart is empty | Verify that submitting checkout with filled form fields (except payment details) allows submit, but shows “Your cart is empty” message when cart has no items. | User is logged in, Cart is empty | 1. Navigate to Checkout Page. 2.Fill all required fields except payment details. 3.Select payment method = Credit Card / PayPal. 4.Click Submit / Place Order | Fill all checkout fields except Credit Card / PayPal details. Select payment method = Credit Card / PayPal | System should prevent submission because payment details are incomplete | User remains on Checkout Page. | System allows submission, but shows “Your cart is empty” message. Checkout is not processed | Failed | Zeina Salem | Sprint 1: Core Flow Execution | High
TC-C-011 | Checkout page | FR-C-11 | Checkout cannot be tested due to inability to add products | Verify that checkout works with items in cart. Test cannot be executed because Products Page is empty and items cannot be added to cart | User is logged in. Products Page shows no items; Cart is empty | 1.Navigate to Products Page. 2.Attempt to add product to cart (not possible). 3.Attempt checkout | N/A | User should be able to add products and submit checkout | User remains on Products / Cart Page | Cannot add items → checkout test cannot be executed | Not_Executed | Zeina Salem | Sprint 1: Core Flow Execution | Critical
TC-C-012 | Order Tracking page | FR-C-12 | Display “No orders found” when user has no order history | Verify that the system shows “No orders found” when the user has no previous orders | User has no orders (cart empty → no checkout happened). | 1. Navigate to the Order Tracking page. | N/A | Message “No orders found” should be displayed | User remains on Order Tracking page. No orders exist. | Message is displayed as expected. | Passed | Zeina Salem | Sprint 1: Core Flow Execution | Medium
TC-C-013 | Order Tracking page | FR-C-12 | “Start Shopping” button does not redirect user | Verify the behavior of the Start Shopping button when there are no order | No orders / Empty cart | 1.Navigate to Order Tracking page. 2. Click “Start Shopping | N/A | User should be redirected to the Products page (Shop) | User remains on Order Tracking page. No navigation occurs | User stays on the same page | Failed | Zeina Salem | Sprint 1: Core Flow Execution | Medium
TC-C-014 | Order Tracking page | FR-C-12 | Order Tracking with existing orders cannot be tested due to inability to place orders | Verify that the Order Tracking page displays user orders when at least one order exists. | User is logged in. Products Page shows no items; Cart is empty. Cart remains empty. No orders can be placed. | 1. Navigate to Products Page. 2. Attempt to add product to cart (not possible). 3. Attempt checkout (not possible). 4. Navigate to Order Tracking page. | N/A | User should be able to see a list of previous orders when at least one order has been placed | User remains unable to create any orders. Order Tracking shows no orders | Cannot add products → cannot place an order → Order Tracking with existing orders cannot be tested | Not_Executed | Zeina Salem | Sprint 1: Core Flow Execution | Critical
TC-S-001 | Support Center page | FR-S-1 | Search Bar - Valid Keyword | Verify that entering a valid keyword returns relevant help content | User is on the Support/Help page | 1. Click on the search input field 2. Enter “Order” 3. Click on Search button | Keyword: Order | Relevant items or suggestions should be displayed | Search results remain displayed | the page reloads, and no relevant items appear | Not_Executed | Sarah Elzeiny | Sprint 1: Core Flow Execution | Medium
TC-S-002 | Support Center page | FR-S-2 | Open Support Ticket Redirection | Verify Open Support Ticket page navigation | User is on Support/Help page | 1. Locate "Open Ticket" button 2. Click on button | N/A | User is redirected to support ticket submission page | Ticket page is loaded with form fields visible | massage appears with "Fill the form below to open a support ticket." | Passed | Sarah Elzeiny | Sprint 1: Core Flow Execution | High
TC-S-003 | Support Center page | FR-S-3 | Support Ticket Form Accessibility | Verify Open Ticket accessibility via keyboard | User on Support page | 1. Hit Tab until Open Ticket button is highlighted 2. Press Enter | N/A | Ticket submission with a message says "Please fill out the form." | User remains on the ticket form section | Ticket submission with a message says "Please fill out the form." | Passed | Sarah Elzeiny | Sprint 1: Core Flow Execution | low
TC-S-004 | Support Center page | FR-S-4 | Start Chat Feature Launch | Ensure that clicking "Start Chat" opens live chat support window | Live chat support system is active | 1. Locate "Start Chat" button 2. Click on button | N/A | Chat window or popup appears for real-time support | N/A | massage appears with "Chat support is offline. Please submit a ticket." | Passed | Sarah Elzeiny | Sprint 1: Core Flow Execution | low
TC-S-005 | Support Center page | FR-S-5 | Call Us Button - Phone Dialing (Mobile) | Verify mobile call initiation from Call Now | N/A | 1. Locate Call Now button 2. Click button | N/A | Mobile dialer opens with support number displayed | Call can be made | massage appears with "Call us at 1-800-123-4567. Support hours: Mon-Fri 9AM-6PM EST." required info | Passed | Sarah Elzeiny | Sprint 1: Core Flow Execution | Medium
TC-S-006 | Support Center page | FR-S-6 | Support Page Content Correctness | Ensure description texts are clear and relevant to support actions | Page is loaded | 1. Read description under each support card 2. Compare with expected purpose | Expected descriptions: ticket, chat, call | Clear, accurate support info visible to users | Page unchanged | Clear, accurate support info visible to users | Passed | Sarah Elzeiny | Sprint 1: Core Flow Execution | Medium
TC-S-007 | Support Center page | FR-S-7 | Support Buttons Not Broken (No 404) | Ensure that clicking any support option doesn’t cause 404 or system error | Internet connected | Click: 1. Open Ticket 2. Start Chat 3. Call Now | N/A | All links open working pages/interfaces | User at correct destination (ticket/chat/dialer) | All links open working pages/interfaces | Passed | Sarah Elzeiny | Sprint 1: Core Flow Execution | Medium

## API Test Cases
TC_ID | Title | Description/Summary | Base URL | Endpoint | HTTPS Method | Input Data(Request data body) | Expected Status | Expected Result(Response Body | Actual Status | Actual Result(Response Body) | Pass/Fail | Author
TC_001 | User Registration with Valid Data | Verify that a new user can successfully register by providing all required fields with valid data , and that the API returns a success response with appropriate user details. | https://cartify.runasp.net/swagger/index.html | /api/Users/Register | POST | email:"User658@gmail.com, password:User_5050",FirstName:"User", LastName:"Example", UserName:"exampleUser", BirthDate:"2025-11-29", Gender:"Female", Telephone:"01234567890" | 200 OK | The API returns a simple success message. | 200 OK | Success | pass | Zeina Salem
TC_002 | User Registration with Missing Required Field (Password) | Verify that the API returns an error when the required field 'password' is not provided during user registration | https://cartify.runasp.net/swagger/index.html | /api/Users/Register | POST | email:"User658@gmail.com, ,FirstName:"User", LastName:"Example", UserName:"exampleUser", BirthDate:"2025-11-29", Gender:"Female", Telephone:"01234567890" | 400 Bad Request | error: "Password is required" | Not executed | The API rejected the request because the required 'password' field is missing. Required fields are highlighted in red in Swagger. | Fail | Zeina Salem
TC_003 | User Login with Valid Credentials | Verify that a registered user can successfully log in by providing valid username/email and password, and that the API returns a success response with the authentication token. | https://cartify.runasp.net/swagger/index.html | /api/Users/Login | POST | Username:"User658@gmail.com", password:"User_5050" | 200 OK | The API returns a success message. An authentication token should be generated for the user | 200 OK | { "jwt": "eyJhbGciOiJIUzI1NiIsInR5cCI6IkpXVCJ9.eyJlbWFpbCI6IlVzZXIyNzZAZ21haWwuY29tIiwic3ViIjoiZjBhMjM5NDUtZjA1Yi00NjcxLTgwM2ItOGQ4OWQ1YjAwYjAxIiwiaHR0cDovL3NjaGVtYXMubWljcm9zb2Z0LmNvbS93cy8yMDA4LzA2L2lkZW50aXR5L2NsYWltcy9yb2xlIjoiVXNlciIsIm5iZiI6MTc2NDQ0NzEzMCwiZXhwIjoxNzY0NDQ4MDMwLCJpc3MiOiJodHRwczovL2NhcnRpZnkucnVuYXNwLm5ldC8iLCJhdWQiOiJodHRwczovL2NhcnRpZnkucnVuYXNwLm5ldC8ifQ.9m2I8CkLutxCZb962h65zDlk9-HioXTUnhgzuvkWrVI", "jwtExpiry": "2025-11-29T20:27:10Z" } | Pass | Zeina Salem
TC_004 | User Login with Missing Password | Verify that the API returns an error when the user attempts to log in without providing the required password | https://cartify.runasp.net/swagger/index.html | /api/Users/Login | POST | Username:"User658@gmail.com" | 400 Bad Request | error: "Password is required" | 400 Bad Request | "errors": { "password": [ "The password field is required." ] | Pass | Zeina Salem
TC_005 | Refresh Access Token with Valid Refresh Token | Verify that a user can obtain a new access token by providing a valid refresh token, and that the API returns a success response with the new access token | https://cartify.runasp.net/swagger/index.html | /api/Users/RefreshToken | POST | None | 200 OK | return a new access token and the expiry time | 200 OK | { "jwt": "eyJhbGciOiJIUzI1NiIsInR5cCI6IkpXVCJ9.eyJlbWFpbCI6IlVzZXIyNzZAZ21haWwuY29tIiwic3ViIjoiZjBhMjM5NDUtZjA1Yi00NjcxLTgwM2ItOGQ4OWQ1YjAwYjAxIiwiaHR0cDovL3NjaGVtYXMubWljcm9zb2Z0LmNvbS93cy8yMDA4LzA2L2lkZW50aXR5L2NsYWltcy9yb2xlIjoiVXNlciIsIm5iZiI6MTc2NDQ0ODQ5OCwiZXhwIjoxNzY0NDQ5Mzk4LCJpc3MiOiJodHRwczovL2NhcnRpZnkucnVuYXNwLm5ldC8iLCJhdWQiOiJodHRwczovL2NhcnRpZnkucnVuYXNwLm5ldC8ifQ.BdB0YQDQF5733cb7ZATehMF9TqTA0QiS-kHjjtWl41A", "jwtExpiry": "2025-11-29T20:49:58Z" } | Pass | Zeina Salem
TC_006 | Reset Password /Check Email and Generate Verification Code | Verify that the system allows the user to request a verification code by entering a valid registered email address | https://cartify.runasp.net/swagger/index.html | /api/Users/ResetPassword/CheckEmailAndGenerateCode | POST | "email": "User658@gmail.com" | 200 OK | generate a verification code successfully | 500 Internal Server Error | The system returned 500 Internal Server Error and did not generate a verification code | Fail | Zeina Salem
TC_007 | Reset Password /Verify Code with Valid Input | Verify that the system accepts and validates a correct verification code | https://cartify.runasp.net/swagger/index.html | /api/Users/ResetPassword/CheckCodeAndChangePassword | POST | None | 200 Ok | confirm that the code is valid | Not executed | valid verification code could not be generated due to failure in the previous step | Not excuted | Zeina Salem
TC_008 | Create Merchant Profile – Successful Creation with Valid Data | Verify that the system successfully creates a merchant profile when all required fields are provided with valid data, and returns a new updated token | https://cartify.runasp.net/swagger/index.html | /api/Users/CreatMerchantProfile | POST | "storeName": "Mega Shop" | 200 OK | The merchant profile should be created successfully. A new token should be generated and returned in the response. | 200 OK | { "jwt": "eyJhbGciOiJIUzI1NiIsInR5cCI6IkpXVCJ9.eyJlbWFpbCI6IlVzZXIyNzZAZ21haWwuY29tIiwic3ViIjoiZjBhMjM5NDUtZjA1Yi00NjcxLTgwM2ItOGQ4OWQ1YjAwYjAxIiwiaHR0cDovL3NjaGVtYXMubWljcm9zb2Z0LmNvbS93cy8yMDA4LzA2L2lkZW50aXR5L2NsYWltcy9yb2xlIjpbIlVzZXIiLCJNZXJjaGFudCJdLCJuYmYiOjE3NjQ0NTE0MjUsImV4cCI6MTc2NDQ1MjMyNSwiaXNzIjoiaHR0cHM6Ly9jYXJ0aWZ5LnJ1bmFzcC5uZXQvIiwiYXVkIjoiaHR0cHM6Ly9jYXJ0aWZ5LnJ1bmFzcC5uZXQvIn0.kJ0SVctFNM0oLNM2gg3XSUpmRBPu1-lndy1s4mRiWb0", "jwtExpiry": "2025-11-29T21:38:45Z" } | Pass | Zeina Salem
TC_009 | Access User Profile with Valid User ID | Verify that the system successfully retrieves a user profile when a valid numeric User ID is provided | https://cartify.runasp.net/swagger/index.html | /api/Profile/{userId} | GET | userId:"[2345] | 200 OK | User profile details are returned successfully | 200 OK | User profile retrieved successfully | Pass | Zeina Salem
TC_010 | Access User Profile with Nonexistent User ID | Verify that the system returns an error when a numeric User ID that does not exist is provided | https://cartify.runasp.net/swagger/index.html | /api/Profile/{userId} | GET | userId:"999/;" | 404 Not found | "User ID not found" or equivalent error message | 404 Not found | "message": "User not found" | Pass | Zeina Salem
TC_011 | Get Order Details by ID | Verify that the system allows fetching the details of an order by providing a valid order ID. | https://cartify.runasp.net/swagger/index.html | /api/Merchant/orders/{orderrId} | GET | orderId:"2053" | 200 OK | display the order details | 500 Internal Server Error | The system returned 500 Internal Server Error. | Fail | Zeina Salem
TC_012 | Update Order Status with Valid Order ID | Verify that the system allows updating the status of an existing order by providing a valid order ID and status value. | https://cartify.runasp.net/swagger/index.html | /api/Merchant/orders/{orderrId}/status | PUT | orderId:"2053" | 200 OK | update the order status successfully | 500 Internal Server Error | The system returned 500 Internal Server Error. | Fail | Zeina Salem
TC_013 | Create Product with Valid Input | Verify that the system allows creating a new product when all required fields are provided with valid data. | https://cartify.runasp.net/swagger/index.html | /api/Merchant/Products | POST | ProductName:"test product", ProductDescription"It's a test product", TypeId:[1], StoreId:[1] | 200 OK | Product should be created successfully | 400 Bad Request | "message": "Failed to create product. Please check your input and try again." | Fail | Zeina Salem
TC_014 | Checkout with Complete Payment and Billing Details | Verify the system behavior when attempting to complete the checkout with all required fields provided | https://cartify.runasp.net/swagger/index.html | /api/Checkout | POST | "userId": 2147483647,productId": 214748364, quantity": 2147483647,price": 0.01,fullName": "UserExample", "email": "User658@gmail.com", "phone": "0101234567890", "address": "45 eltahrir", "city": "Giza", "country": "Egypt", "postalCode": "12655" , "paymentMethod": "CreditCard", "cardNumber": "4111111111111", "cardHolder": "user example","expiryDate": "11/26", "cvv": "456" | 200 OK | the order should be placed successfully | 400 Bad Request | "success": false, "message": "Checkout failed: An error occurred while saving the entity changes. See the inner exception for details." | Fail | Zeina Salem

## SIQs
SIQ_ID | Req_ID | Requirement | SIQs | Status | Answer

## Traceability
Req_ID | Linked_TestCases

## Bug_Report
Bug ID | Module / Feature | Title / Summary | Reported By | Detected In / Test Cycle | Bug Type | Severity | Priority | Environment | TC_ID | Req_ID/US_ID | Description | Steps to Reproduce | Expected Result | Actual Result | Attachments / Evidence | Status | Assigned To | Detected By | Date Logged | Comments / Root Cause
PROD-001 | Products Page | Search and Go to Cart buttons overlap on MD screens (875px and below) | Eslam Elhosuniy | V_1.0 |  | Minor | Low |  |  |  | An overlap occurs between the Search button and the Go to Cart button | 1. Open the Products page. 2. Open Developer Tools (F12). 3. Select Responsive Mode or manually resize the browser window. 4. Set the screen width to a value between 900px and 867px. | The "Search" and "Go to Cart" buttons should remain separated by a clear space | The Search button and Go to Cart button overlap at a screen | https://drive.google.com/file/d/1Wj_GvzymR-Y9TJeqAWRcq3dLNDKLbSI-/view?usp=sharing | New
PROD-002 | Products Page | Excessive and aimless blank space present below the product grid | Eslam Elhosuniy | V_1.0 |  | Minor | Low |  |  |  | There is a very large amount of redundant white space at the bottom of the product listing page, below the pagination controls. | 1. Open the Products page. 2. Scroll to the bottom of the page. | The page content should end naturally without this excessive blank space | A large, unjustified white space is present, extending to the bottom of the viewport/page. | https://drive.google.com/file/d/1-sz1QMCKFeDi44-uSQO7BjlGbTd16xYI/view?usp=sharing | New
PROD-003 | Products Page | "Sort By" button is inaccessible | Eslam Elhosuniy | V_1.0 |  | Critical | High |  |  |  | In mobile viewports, the Sort By button is positioned underneath the fixed/sticky top navigation bar (Navbar). This overlap causes the "Sort By" button to be partially or completely invisible and inaccessible | 1. Open the Products page. 2. Set the viewport width to simulate a mobile device (e.g., less than 768px). | The "Sort By" button element must be positioned with sufficient clearance (Margin/Padding) below the sticky Navbar to ensure it is fully visible and accessible/clickable in mobile view. | The "Sort By" button is inaccessible because it is covered by the fixed/sticky top navigation bar. | https://drive.google.com/file/d/1pFJm0kTp41RTFoWbz-rMU38wl5TljkVw/view?usp=drive_link | New
PROD-004 | Products Page | "Previous" and "Next" button out of this controllers | Eslam Elhosuniy | V_1.0 |  | Minor | Low |  |  |  | In the mobile viewport, the text for the "Previous" and "Next" buttons in the pagination component is not fully displayed | 1. Open the Products page. 2. Adjust the viewport width to a narrow mobile size . 3. Scroll down to the bottom of the product list to view the pagination control. | The full text, "Previous" and "Next," should be clearly visible and centered within their respective buttons | "Previous" and "Next" button not centered within their respective buttons | https://drive.google.com/file/d/1t5DgfajDpemuqFdHyoIXHFg_sb8SOugd/view?usp=drive_link | New
PROD-005 | Products Page | Search button only triggers a page refresh instead of filtering products based on the query | Eslam Elhosuniy | V_1.0 |  | Critical | High |  |  |  | When a user enters a search query and clicks the "Search" button, the page simply refreshes without performing the actual search |  |  |  | https://drive.google.com/file/d/1GZDk8f9Y5FHG-WUPWRuFWRboi2dOf42G/view?usp=drive_link | New
PROD-006 | Products Page | Product sorting by Rating becomes incorrect after navigating back from a detail page | Eslam Elhosuniy | V_1.0 |  | Medium | Medium |  |  |  | When the user applies sorting by Rating and then navigates away to a product detail page and uses the browser's Back button to return, the products are displayed in an incorrect order. | 1. Navigate to the Products page. 2. Use the "Sort By" dropdown and select sorting by "Rating". 3. Click on any product card to navigate to its Product Detail Page. 4. Use the browser's Back button to return to the Products page. | Upon returning to the Products page using the browser's Back button, the product list should still be correctly sorted by Rating as it was before navigation. | The products are displayed in an incorrect/default order, despite the sorting filter being visually selected as "Rating." | https://drive.google.com/file/d/1ADBnxVkgR70E0IudScOKL-LikHkT8489/view?usp=drive_link | New
PRD-001 | Products details | Product Image Not Loading Correctly | Eslam Elhosuniy | V_1.1 |  | Medium | High |  |  |  | When the user opens the product Details page, the product image not loading | 1. Navigate to the Products page. 2. Click on any product card to navigate to its Product Detail Page. | The actual product image should load clearly. It should not show a broken link icon or alt text only. | The products are displayed, But image not load. |  | New
CART-001 | Cart page | Added products do not replace or update default items in the cart | Zeina | V_1.0 |  | Critical | High |  |  |  | When a user adds a product from the Shop page, the cart content does not update. Instead, it always shows three default items that never change | 1. Go to the shop page 2. Click "Add to cart" for any product 3. Navigate to the cart page | The cart should display only the products the user selected from the Shop page | The cart always shows three predefined products, regardless of user actions | https://drive.google.com/file/d/1UWnjiZDWCEW0udRdy2JSiPcDJuN2dyNV/view?usp=sharing | New
CART-002 | Cart page | Cart always displays three fixed products even when no items are added | Zeina | V_1.0 |  | Major | High |  |  |  | When the user opens the Cart page without adding any products, three fixed products are displayed by default. This misleads users into thinking these items were added to the cart | 1. Navigate the website 2. Without adding any product to the cart, open the cart page. 3. observe the displayed items | The Cart should be empty when no products are added | The Cart shows three fixed products by default, even though the user did not add them | https://drive.google.com/file/d/1rP2lkiE6v-tNNIHsGZACpy2vkcyIngmg/view?usp=sharing | New
CART-003 | Cart page | Increasing product quantity updates total price but not item count | Zeina | V_1.0 |  | Medium | High |  |  |  | When the user increases the quantity of a product in the cart, the total price is updated correctly, but the item count displayed in the cart remains the same | 1. Open the Cart page 2. Increase the quantity of any product using the'+' button. 3. Ckeck the total price and item count. | Both the total price and the cart item count should update according to the new quantity | The total price changes, but the number of items shown in the cart remains unchanged | https://drive.google.com/file/d/1q0OXRbiZ91bD4jlV3EneGTLmZJjHrk6m/view?usp=sharing | New
CART-004 | Cart page | “Proceed to Checkout” button is not functional | Zeina | V_1.0 |  | Critical | High |  |  |  | The “Proceed to Checkout” button on the Cart page is unresponsive. When clicked, it does not redirect the user to the checkout page or trigger any visible action | 1. Add any product to the cart 2. Open the cart page 3. Click the 'Proceed to Ckeckout' button | The user should be redirected to the Checkout page to complete the purchase process | The button does nothing — no redirection or feedback is shown | https://drive.google.com/file/d/1sI18_dC2F1fe627Jz3OiZHh7Y35SYErJ/view?usp=sharing | New
CART-005 | Cart page | “Continue Shopping” button redirects back to the Cart page instead of the Shop page | Zeina | V_1.0 |  | Medium | Medium |  |  |  | When clicking the “Continue Shopping” button on the Cart page, the user is redirected back to the same Cart page instead of returning to the Shop or Products page | 1. Open the cart page 2. Click the 'Continue Shopping' button | The user should be redirected to the Shop/Products page to continue browsing and adding more items | The user is redirected back to the Cart page | https://drive.google.com/file/d/13soIjx6q7rhoLZEzlrDHIlmboGxKJrZI/view?usp=sharing | New
CHK-001 | Checkout page | Payment method validation missing — order is submitted even if no payment method is selected | Zeina | V_1.0 |  | Medium | High |  |  |  | When submitting the checkout form without selecting any payment method, the system still shows a success message (“Data Submitted successfully”) instead of prompting the user to choose a payment option | 1. Go to the Checkout page 2. Fill in all required fields except the payment method 3. Click the 'Submit' button | A validation message should appear, prompting the user to select a payment method before proceeding | The form is submitted successfully even though no payment method is selected | https://drive.google.com/file/d/1w_v_uQvl-3AqN8fv2TFfQGgeAcdpBHFp/view?usp=sharing | New
TRK-001 | Tracking page | “View Details” button shows a static message without displaying product details | Zeina | V_1.0 |  | Low | Medium |  |  |  | Clicking the “View Details” button on any order displays the message “Viewing product details,” but no product information or details are actually shown on the screen. | 1. Go to the Order Tracking page 2. Scroll to any order under "All Orders", "Active", "Completed". 3. Click the 'View Details' button. | A detailed view or popup should appear showing complete information about the selected order (e.g., product name, quantity, price, delivery status, etc.) | A static text message “Viewing product details” appears, but no product details or additional information are displayed | https://drive.google.com/file/d/1xzpl_8XSFOThu24mJ0w1WiL_Jxtr3xK-/view?usp=sharing | New
New
BUG-U-001 | User State Management (Login/Header) | User State Not Persisted After Successful Login (Header Still Shows 'Start for free') | Abdallah Mohamed | Sprint 1: Core Flow Execution V_1.0 | Functional / Security | P1/Critical | High | Windows/Chrome | Discovery Flow | FR-U-001, FR-U-002 | After successful login, the application fails to update the global header state. The navigation still shows "Start for free" and "Login," allowing re-login while authenticated. | 1. Navigate to login.html and log in. 2. Observe the header after redirection to the homepage. 3. Check the header bar and the hamburger menu options. | The header should display authenticated options (Profile, Logout) and the "Start for free" link should disappear. | The "Start for free" and "Login" options remain visible, allowing the user to click "Login" and repeat the process. | ScreenCast | New | (Dev Lead) | Abdallah Mohamed | 2025-11-09 | Suspect root cause is a client-side state management issue.
BUG-U-002 | User Pages / Profile Access | Profile Page Access Denied Despite Being Logged In | Abdallah Mohamed | Sprint 1: Core Flow Execution V_1.0 | Functional / State Management | P1/Critical | High | Windows/Chrome | TC-U-1.3, TC-U-3.3 | FR-U-003, FR-A-013 | After a successful login, attempting to navigate to the Profile page fails. The system displays a pop-up message stating the user needs to log in first, blocking access to all profile features. | 1. Log in successfully. 2. Click the Profile link (from the header/menu). | The user should be redirected to profile.html, displaying their personal information. | A pop-up/error message appears stating the user must log in, blocking the profile page view. | ScreenCast | New | (Dev Lead) | Abdallah Mohamed | 2025-11-09 | Linked to BUG-U-001. The profile component is not correctly reading the global authenticated state.
BUG-U-003 | Password Recovery | Password Recovery Process Fails Immediately with Server Error | Abdallah Mohamed | Sprint 1: Core Flow Execution V_1.0 | Functional | P1/Critical | High | Windows/Chrome | TC-U-1.4 | FR-U-004 | The user is unable to initiate the password recovery process. After entering a valid registered email and submitting, a hard error message appears, preventing the system from sending the recovery link. | 1. Navigate to the "Forgot Password" link/page. 2. Enter a valid, registered email address. 3. Click 'Submit'/'Recover'. | A confirmation message displays, stating that a recovery link has been sent to the specified email address. | An error message appears: "❌ Enter a valid email or server error," immediately blocking the process. | ScreenCast | New | (Dev Lead) | Abdallah Mohamed | 2025-11-09 | Suspect failure in the form submission handling or API endpoint integration.
BUG-U-004 | Multi-step Registration (Personal Info Form) | Missing Input Validation: Phone Number Accepts Alphabetic Characters | Abdallah Mohamed | Discovery Flow (During TC-U-1.1 execution) V_1.0 | Data Validation | P2/Major | Medium | Windows/Chrome | Discovery Flow | (Implied Data Integrity) | In the second step of registration (Personal Info Form), the Phone Number input field accepts and submits alphabetic characters and values significantly shorter than a standard phone number (e.g., '1'). | 1. Navigate to the Personal Info form. 2. Attempt to type alphabetic characters (e.g., 'abc') into the Phone Number field. 3. Attempt to enter a single digit (e.g., '1') and submit. | The field should restrict input to numerical digits (0-9) and enforce a minimum valid length before submission. | The field accepts alphabetic characters and submits with single-digit input. | ScreenCast | New | (Dev Team) | Abdallah Mohamed | 2025-11-09 | Frontend input masking and validation are missing or improperly configured.
SUP-CHAT-UI-001 | Support Center | Visual UI Error in Chat Window When Clicking "Start Chat" Button | Sarah Elzeiny | Discovery Flow (During TC-U-1.1 execution) V_1.0 | Visual Content | Low | Low | Windows/Chrome |  |  | When the user clicks the Start Chat button on the Support Page, the chat window opens but appears with visual errors, including misalignment, possible broken layout, overlapping elements, or incorrect styling. | Open the Support Page. Click the Start Chat button. Observe the chat window that appears. | Chat window should open with correct alignment, readable text, proper spacing, no overlap, and clean visual design. | Chat window opens but appears partially broken with visual/UI defects such as: Misaligned content Overlapping elements Possible missing container styles Typography and spacing issues | Screenshot (505).png | New | (Dev Team) | Sarah Elzeiny | 25/11/2024

## Summary_Report
Req_ID | Linked Test Cases | Coverage Status
|  |  | Total Req's | Covered | Not_Covered | Approved | Rejected | Coverage Percentage